## Defects found
Defect ID | Steps To Reproduce | Expected Result | Actual Result | Test Case ID | Severity | Priority | Tested on Build Version ID | Date Raised | Raised By | Status | Summary
D1 | 1. click on new customer | New customer should be | connection error | TC7 | High | High | V1 | 20/08/2023 | Henry | Open | New customer was not created. Connection error message is displayed as follows:
| 2. enter valid data in the fields. | created | [8 empty] | Connection failed: Access denied for user 'root'@'localhost' (using password: NO)
customer name = HenryAgulanna, gender = male
date of birth = 10/20/1982, address = Street 25 westbrom,
city = west bromwich, state =
west midlands, pin = 101982, mobile number =
01234567890, email = agulannah@gmail.com
3. click on submit
D2 | check the name of the website | Guru99 Bank | Gtpl Bank | Exploratory Testing | Low | High | V1 | 20/08/2023 | Henry | Open | The name of the website should be Guru99 Bank but it displayed Gtpl Bank
D3 | 1. click on balance enquiry | user can check balance using | blank page displayed | TC12 | High | High | V2 | 24/08/2023 | Henry | Open | user could not check balance using valid account number. Blank page is displayed
| 2. enter valid account number - 125902, 126113 | valid account number
3. click on submit
D4 | 1. click on customized statement | user can see customized statement | Error message: | TC16 | High | High | V2 | 24/08/2023 | Henry | Open | user could not see customized statement using valid data
| 2. enter valid data in the fields | using valid data in the fields | Account does not exist | [7 empty] | Error message: Account does not exist
account number = 125902, from date = 19/08/2023,
to date = 24/08/2023, minimum transaction value = 100,
number of transaction = 5
D5 | 1. click on mini statement | user can see mini statement of | blank page is displayed | TC55, C10 | High | High | V2 | 25/08/2023 | Henry | Open | user could not see mini statement using valid account number
| 2. enter valid account number and | last 5 transactions of an account using
| submit. account number = 125902 | valid account number
D6 | 1. click on edit customer | customer can be edited using valid | customer is successfully edited | TC38 | Low | low | V2 | 26/08/2023 | Henry | Open | customer is successfully edited but there is error message: 'No Changes made to
| 2. enter valid customer ID = 949 | customer ID | with error message: No Changes | [7 empty] | customer records'
| 3. click on submit |  | made to Customer records
D7 | 1. click on edit account | Form after submitting Edit Account should | blank page is displayed | TC34 | High | High | V2 | 26/08/2023 | Henry | Open | Form after submitting Edit Account did not display
| 2. enter account number = 125902 | be displayed and data is edited successfully
3. click on submit
D8 | 1. click on edit account | Form after submitting Edit Account should | blank page is displayed | TC37.1 | High | High | V2 | 26/08/2023 | Henry | Open | Form after submitting Edit Account did not display
| 2. enter valid account number = 125902 | be displayed and customer ID and balance
| 3. click on submit | disabled
D9 | 1. click on delete customer | customer with no active account can | Customer could not be deleted | TC25 | High | High | V2 | 26/08/2023 | Henry | Open | Customer could not be deleted
| 2. enter valid customer ID = 949 | be deleted
3. click on submit
D10 | 1. click on delete account | customer's account should be deleted using | Account could not be deleted | TC21 | High | High | V2 | 26/08/2023 | Henry | Open | customer's account could not be deleted using valid account number
| 2. enter valid account number = 125902 | valid account number
3. click on submit
D11 | click on Home to check if user can return to home page | user should return to home page when clicking | error message is displayed | Exploratory Testing | Low | High | V2 | 26/08/2023 | Henry | Open | user could not return to home page when clicking on Home
on Home
D12 | 1. click on balance enquiry | user should not see another customer's | blank page displayed | C4.1 | High | High | V3 | 28/03/2023 | Henry | Open | blank page is displayed while user is checking another customer's balance
| 2. enter another customer's account | account balance with error mesaage: you are
| number | not authorized to get balance details of this
| 3. click on submit | account
D13 | 1. click on fund transfer | fund should be transferred successfully with | Fund Transafer Details for Account | Exploratory Testing | Low | Low | V3 | 28/08/2023 | Henry | Open | spelling mistake when fund is successfully tranferred
| 2. enter valid data in the fields and | no spelling mistake on the message | No: 126189
note in the description field
D14 | 1. click on fund transfer | user cannot transfer fund when | fund is transferred | TC44, C8 | High | High | V3 | 28/08/2023 | Henry | Open | fund transferred when the payer's and payee's account numbers are the same
| 2. enter the same account number | payer's account number and payee's account
| in the payer's and payee's fields | number are the same
3. enter the amount and description
4. click on submit
D15 | 1. click on fund transfer | user should not transfer fund from | fund transferred | C9.1 | High | High | V3 | 28/08/2023 | Henry | Open | user transferred fund from another customer's account to user's account
| 2. enter another customer's account | another customer's account to user's
| number then user's account number | account
3. enter amount and note on the
description field
4. click on submit
D17 | 1. click on deposit | user should deposit money | blank page displayed | TC30 | High | High | V3 | 28/08/2023 | Henry | Open | blank page is displayed while user is depositing money
2. enter valid data in the fields
3. enter note on the description field
4. click on submit
D18 | 1. click on withdrwal | user should withdraw money | blank page displayed | TC65 | High | High | V3 | 28/082023 | Henry | Open | blank page is displayed while user is withdrawing money
2. enter the account number
3. enter amount
4. add note on the description and submit
D19 | 1. click on withdrwal | user cannot withdraw money using | blank page displayed | TC70 | High | High | V3 | 28/08/2023 | Henry | Open | blank page is displayed while user is withdrawing money using insufficient amount
| 2. enter account number and insufficient amount, | insufficient amount
add note on the description field and submit

## Fixed defects
Defect ID | Steps To Reproduce | Expected Result | Actual Result | Test Case ID | Severity | Priority | Fixed on Build Version ID | Date Raised | Raised By | Status | Summary | Date Fixed
D1 | 1. click on new customer | New customer should be | connection error | TC7 | High | High | V2 | 20/08/2023 | Henry | closed | New customer was not created. Connection error message is displayed as follows: | 21/08/2023
| 2. enter valid data in the fields. | created | [8 empty] | Connection failed: Access denied for user 'root'@'localhost' (using password: NO)
customer name = HenryAgulanna, gender = male
date of birth = 10/20/1982, address = Street 25 westbrom,
city = west bromwich, state =
west midlands, pin = 101982, mobile number =
01234567890, email = agulannah@gmail.com
3. click on submit
D2 | check the name of the website | Guru99 Bank | Gtpl Bank | Exploratory Testing | Low | High | V2 | 20/08/2023 | Henry | closed | The name of the website should be Guru99 Bank but it displayed Gtpl Bank | 21/08/2023
D3 | 1. click on balance enquiry | user can check balance using | blank page displayed | TC12 | High | High | V3 | 24/08/2023 | Henry | closed | user could not check balance using valid account number. Blank page is displayed | 26/08/2023
| 2. enter valid account number - 125902, 126113 | valid account number
3. click on submit
D12 | 1. click on balance enquiry | user should not see another customer's | blank page displayed | C4.1 | High | High | V4 | 28/03/2023 | Henry | closed | blank page is displayed while user is checking another customer's balance | 29/08/2023
| 2. enter another customer's account | account balance with error mesaage: you are
| number | not authorized to get balance details of this
| 3. click on submit | account
D14 | 1. click on fund transfer | user cannot transfer fund when | fund is transferred | TC44, C8 | High | High | V4 | 28/08/2023 | Henry | closed | fund transferred when the payer's and payee's account numbers are the same | 29/08/2023
| 2. enter the same account number | payer's account number and payee's account
| in the payer's and payee's fields | number are the same
3. enter the amount and description
4. click on submit
D15 | 1. click on fund transfer | user should not transfer fund from | fund transferred | C9.1 | High | High | V4 | 28/08/2023 | Henry | closed | user transferred fund from another customer's account to user's account | 29/08/2023
| 2. enter another customer's account | another customer's account to user's
| number then user's account number | account
3. enter amount and note on the
description field
4. click on submit
D5 | 1. click on mini statement | user can see mini statement of | blank page is displayed | TC55, C10 | High | High | V3 | 25/08/2023 | Henry | closed | user could not see mini statement using valid account number | 29/08/2023
| 2. enter valid account number and | last 5 transactions of an account using
| submit. account number = 125902 | valid account number
D4 | 1. click on customized statement | user can see customized statement | Error message: | TC16 | High | High | V4 | 24/08/2023 | Henry | closed | user could not see customized statement using valid data | 29/08/2023
| 2. enter valid data in the fields | using valid data in the fields | Account does not exist | [7 empty] | Error message: Account does not exist
account number = 125902, from date = 19/08/2023,
to date = 24/08/2023, minimum transaction value = 100,
number of transaction = 5
D10 | 1. click on delete account | customer's account should be deleted using | Account could not be deleted | TC21 | High | High | V4 | 26/08/2023 | Henry | closed | customer's account could not be deleted using valid account number | 29/08/2023
| 2. enter valid account number = 125902 | valid account number
3. click on submit
D9 | 1. click on delete customer | customer with no active account can | Customer could not be deleted | TC25 | High | High | V4 | 26/08/2023 | Henry | closed | Customer could not be deleted | 29/08/2023
| 2. enter valid customer ID = 949 | be deleted
3. click on submit
D17 | 1. click on deposit | user should deposit money | blank page displayed | TC30 | High | High | V4 | 28/08/2023 | Henry | closed | blank page is displayed while user is depositing money | 30/08/2023
2. enter valid data in the fields
3. enter note on the description field
4. click on submit
D7 | 1. click on edit account | Form after submitting Edit Account should | blank page is displayed | TC34 | High | High | V4 | 26/08/2023 | Henry | closed | Form after submitting Edit Account did not display | 30/082023
| 2. enter account number = 125902 | be displayed and data is edited successfully
3. click on submit
D8 | 1. click on edit account | Form after submitting Edit Account should | blank page is displayed | TC37.1 | High | High | V4 | 26/08/2023 | Henry | closed | Form after submitting Edit Account did not display | 30/08/2023
| 2. enter valid account number = 125902 | be displayed and customer ID and balance
| 3. click on submit | disabled
D6 | 1. click on edit customer | customer can be edited using valid | customer is successfully edited | TC38 | Low | low | V4 | 26/08/2023 | Henry | closed | customer is successfully edited but there is error message: 'No Changes made to | 30/08/2023
| 2. enter valid customer ID = 949 | customer ID | with error message: No Changes | [7 empty] | customer records'
| 3. click on submit |  | made to Customer records
D18 | 1. click on withdrwal | user should withdraw money | blank page displayed | TC65 | High | High | V4 | 28/082023 | Henry | closed | blank page is displayed while user is withdrawing money | 30/08/2023
2. enter the account number
3. enter amount
4. add note on the description and submit
D19 | 1. click on withdrwal | user cannot withdraw money using | blank page displayed | TC70 | High | High | V4 | 28/08/2023 | Henry | closed | blank page is displayed while user is withdrawing money using insufficient amount | 30/08/2023
| 2. enter account number and insufficient amount, | insufficient amount
add note on the description field and submit
D11 | click on Home to check if user can return to home page | user should return to home page when clicking | error message is displayed | Exploratory Testing | Low | High | V3 | 26/08/2023 | Henry | closed | user could not return to home page when clicking on Home | 29/08/2023
on Home
D13 | 1. click on fund transfer | fund should be transferred successfully with | Fund Transafer Details for Account | Exploratory Testing | Low | Low | V4 | 28/08/2023 | Henry | closed | spelling mistake when fund is successfully tranferred | 30/08/2023
| 2. enter valid data in the fields and | no spelling mistake on the message | No: 126189
note in the description field